## Submittals
Activity Name | Activity ID | Start | Finish | Longest Path | TF
Secured Area Access Post (SAAP) & Enabling Projects May 2020 |  | 01-Jan-20 A | 2022-01-04 |  | -127
Submittals |  | 01-Jan-20 A | 2020-09-28 |  | 240
Post Mob (30 CD +) |  | 28-Jan-20 A | 2020-09-28 |  | 105
Prefabricated Buildings |  | 03-Feb-20 A | 2020-09-08 |  | -15
P/S_Prefabricated Building | SL3650 | 03-Feb-20 A | 2020-06-29 | No | -15
R/A_Prefabricated Building | SL7800 | 2020-06-30 | 2020-07-28 | No | -15
R/A_Prefabricated Building by California Housing | SL8500 | 2020-07-29 | 2020-09-08 | No | -15
Canopy Insulated Panels |  | 2020-06-01 | 2020-07-28 |  | 82
P/S_canopy insulated panels | SL3500 | 2020-06-01 | 2020-06-29 | No | 82
R/A_canopy insulated panels | SL7650 | 2020-06-30 | 2020-07-28 | No | 82
TC Plan - World Way West Single and Double Lane Closures |  | 2020-06-01 | 2020-07-28 |  | -70
P/S_TC Plan - World Way West Single and Double Lane Closure West Side | SL3350 | 2020-06-01 | 2020-06-29 | No | -70
R/A_TC Plan - World Way West Single and Double Lane Closure West Side | SL7500 | 2020-06-30 | 2020-07-28 | No | -70
Vehicular Traffic & Pedestrian Traffic Evacuation Plan |  | 2020-06-01 | 2020-07-28 |  | 74
P/S_Vehicular Traffic & Pedestrian Traffic Evacuation Plan | SL300 | 2020-06-01 | 2020-06-29 | No | 74
R/A_Vehicular Traffic & Pedestrian Traffic Evacuation Plan | SL4450 | 2020-06-30 | 2020-07-28 | No | 74
Roof Membrane at Canopy |  | 2020-06-01 | 2020-07-28 |  | 149
P/S_Roof Membrane for Canopy | SL4150 | 2020-06-01 | 2020-06-29 | No | 149
R/A_Roof Membrane for Canopy | SL8300 | 2020-06-30 | 2020-07-28 | No | 149
TC Plan - World Way West Crossings at Admin West, LAX Fuel, East End, Maintenance Rd |  | 2020-06-01 | 2020-07-28 |  | -68
P/S_TC Plan - World Way West Single and Double Lane Closure East Side | SL3400 | 2020-06-01 | 2020-06-29 | No | -68
R/A_TC Plan - World Way West Single and Double Lane Closure East Side | SL7550 | 2020-06-30 | 2020-07-28 | No | -68
Pump House Louvers |  | 03-Feb-20 A | 2020-06-29 |  | 54
P/S_Pump House Louvers | SL3550 | 03-Feb-20 A | 07-May-20 A | No
R/A_Pump House Louvers | SL7700 | 2020-06-01 | 2020-06-29 | No | 54
Jack and Bore - Phasing and Sequencing Plan |  | 03-Feb-20 A | 16-Apr-20 A
P/S_Jack and Bore Phasing and Sequencing Plan | SL4200 | 03-Feb-20 A | 25-Mar-20 A | No
R/A_Jack and Bore Casing and Sequencing Plan | SL8350 | 25-Mar-20 A | 16-Apr-20 A | No
Jack and Bore Casing |  | 2020-06-01 | 2020-07-28 |  | -73
P/S_Jack and Bore Casing | SL4100 | 2020-06-01 | 2020-06-29 | No | -73
R/A_Jack and Bore Casing | SL8250 | 2020-06-30 | 2020-07-28 | No | -73
Pump House Exhaust Fans |  | 03-Feb-20 A | 2020-06-29 |  | 77
P/S_Pump House Exhaust Fans | SL3600 | 03-Feb-20 A | 07-May-20 A | No
R/A_Pump House Exhaust Fans | SL7750 | 2020-06-01 | 2020-06-29 | No | 77
Signal Pole and Controller Materials |  | 2020-06-01 | 2020-07-28 |  | -80
P/S_Signal Pole and Controller | SL4250 | 2020-06-01 | 2020-06-29 | No | -80
R/A_Signal Pole and Controller | SL8400 | 2020-06-30 | 2020-07-28 | No | -80
IT & Camera Materials |  | 2020-06-01 | 2020-07-28 |  | 83
P/S_IT & Camera Materials | SL4300 | 2020-06-01 | 2020-06-29 | No | 83
R/A_IT & Camera Materials | SL8450 | 2020-06-30 | 2020-07-28 | No | 83
Vista Paint |  | 28-Jan-20 A | 18-Feb-20 A
P/S_Vista Paint | SL350 | 28-Jan-20 A | 28-Jan-20 A | No
R/A_Vista Paint | SL4500 | 28-Jan-20 A | 18-Feb-20 A | No
Utility Protection Plan |  | 2020-06-01 | 2020-07-28 |  | -43
P/S_Utility Protection Plan | SL500 | 2020-06-01 | 2020-06-29 | No | -43
R/A_Utility Protection Plan | SL4650 | 2020-06-30 | 2020-07-28 | No | -43
Crane Set Up Plan |  | 2020-06-01 | 2020-07-28 |  | -55
P/S_Crane Set Up Plan | SL200 | 2020-06-01 | 2020-06-29 | No | -55
R/A_Crane Set Up Plan | SL4350 | 2020-06-30 | 2020-07-28 | No | -55
PCC Mix Designs |  | 2020-06-01 | 2020-07-28 |  | -56
P/S_PCC Mix Designs | SL250 | 2020-06-01 | 2020-06-29 | No | -56
R/A_PCC Mix Designs | SL4400 | 2020-06-30 | 2020-07-28 | No | -56
24" Fire Water |  | 2020-07-31 | 2020-09-28 |  | -68
P/S_24" FW | SL8550 | 2020-07-31 | 2020-08-28 | No | -68
R/A_24" FW | SL8600 | 2020-08-31 | 2020-09-28 | No | -68
Mobilization Submitals (Within The First 0 to 30 Calendar Days) |  | 01-Jan-20 A | 2020-08-24 |  | 265
Cosco A/C Fire Pump |  | 03-Feb-20 A | 03-Mar-20 A
P/S_Cosco A/C Fire Pump | SL750 | 03-Feb-20 A | 02-Mar-20 A | No
R/A_Cosco A/C Fire Pump | SL4900 | 03-Mar-20 A | 03-Mar-20 A | No
Griffith Labor Rates |  | 03-Feb-20 A | 2020-06-29 |  | 295
P/S_Griffith Labor Rates | SL850 | 03-Feb-20 A | 06-Mar-20 A | No
R/A_Griffith Labor Rates | SL5000 | 2020-06-01 | 2020-06-29 | No | 295
Contractor 24 Hr on Call Personnel |  | 2020-06-01 | 2020-07-28 |  | -82
P/S_Contractor 24hr On Call Personnel | SL1300 | 2020-06-01 | 2020-06-29 | No | -82
R/A_Contractor 24hr On Call Personnel | SL5450 | 2020-06-30 | 2020-07-28 | No | -82
QC Manager |  | 03-Feb-20 A | 19-Feb-20 A
P/S_QC Manager | SL900 | 03-Feb-20 A | 06-Feb-20 A | No
R/A_QC Manager | SL5050 | 07-Feb-20 A | 19-Feb-20 A | No
Baseline Schedule |  | 03-Feb-20 A | 27-May-20 A
P/S_Baseline Schedule 1 | A16680 | 03-Feb-20 A | 03-Mar-20 A | No
R/A_Baseline Schedule 1 | A16690 | 27-Feb-20 A | 26-Mar-20 A | No
P/S_Baseline Schedule 2 | A16700 | 26-Mar-20 A | 02-Apr-20 A | No
R/A_Baseline Schedule 2 | A16730 | 03-Apr-20 A | 15-Apr-20 A | No
P/S_Baseline Schedule 3 | A16720 | 15-Apr-20 A | 24-Apr-20 A | No
R/A_Baseline Schedule 3 | A16710 | 24-Apr-20 A | 13-May-20 A | No
P/S_Baseline Schedule 4 | SL1350 | 14-May-20 A | 20-May-20 A | No
R/A_Baseline Schedule 4 | SL5500 | 21-May-20 A | 27-May-20 A | No
Ductile Iron Fittings-30 inch |  | 27-Jan-20 A | 06-Feb-20 A
P/S_Ductile Iron Fittings - 30 Inch | SL3000 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_Ductile Iron Fittings - 30 Inch | SL7150 | 04-Feb-20 A | 06-Feb-20 A | No
EBAA Mega Lug Restraints |  | 27-Jan-20 A | 06-Feb-20 A
P/S_EBAA Mega Lug Restraints | SL3250 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_EBAA Mega Lug Restraints | SL7400 | 04-Feb-20 A | 06-Feb-20 A | No
Pipe Support / Hangers 2inch to 12inch |  | 27-Jan-20 A | 06-Feb-20 A
P/S_Pipe Support Hangers 2 inch to 12 inch | SL3300 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_Pipe Support Hangers 2 inch to 12 inch | SL7450 | 04-Feb-20 A | 06-Feb-20 A | No
Project Scheduler |  | 03-Feb-20 A | 24-Feb-20 A
P/S_Project Scheduler | SL950 | 03-Feb-20 A | 07-Feb-20 A | No
R/A_Project Scheduler | SL5100 | 10-Feb-20 A | 24-Feb-20 A | No
Traffic Control Plan Per Phase |  | 03-Feb-20 A | 17-Apr-20 A
P/S_Traffic Control Plan and Phase 1 | A16740 | 03-Feb-20 A | 13-Mar-20 A | No
R/A_Traffic Control Plan and Phase 1 | A16750 | 03-Mar-20 A | 13-Apr-20 A | No
P/S_Traffic Control Plan and Phase 2 | SL2400 | 14-Apr-20 A | 15-Apr-20 A | No
R/A_Traffic Control Plan and Phase 2 | SL6550 | 16-Apr-20 A | 17-Apr-20 A | No
Ductile Iron Spools - 40 Inch to 12 Inch |  | 27-Jan-20 A | 06-Feb-20 A
P/S_Ductile Iron Spools - 40 Inch to 12 Inch | SL3100 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_Ductile Iron Spools - 40 Inch to 12 Inch | SL7250 | 28-Jan-20 A | 06-Feb-20 A | No
Ductile Iron Spools - 30 Inch |  | 27-Jan-20 A | 06-Feb-20 A
P/S_Ductile Iron Spools - 30 Inch | SL3150 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_Ductile Iron Spools - 30 Inch | SL7300 | 28-Jan-20 A | 06-Feb-20 A | No
Pressure Reducing Valves 4inch, 10inch, 12inch |  | 27-Jan-20 A | 06-Feb-20 A
P/S_Pressure Reducing Valves 4inch, 10inch, 12ich | SL550 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_Pressure Reducing Valves 4inch, 10inch, 12ich | SL4700 | 28-Jan-20 A | 06-Feb-20 A | No
Demolition Work plan |  | 03-Feb-20 A | 14-Apr-20 A
P/S_Demolition Work Plan | SL1250 | 03-Feb-20 A | 13-Mar-20 A | No
R/A_Demolition Work Plan | SL5400 | 03-Mar-20 A | 14-Apr-20 A | No
HMMP (Hazardous Materials Management Plan) |  | 03-Feb-20 A | 23-Apr-20 A
P/S_HMMP 1 | A16760 | 03-Feb-20 A | 17-Mar-20 A | No
R/A_HMMP 1 | A16770 | 18-Mar-20 A | 21-Apr-20 A | No
P/S_HMMP 2 | SL2450 | 21-Apr-20 A | 22-Apr-20 A | No
R/A_HMMP 2 | SL6600 | 22-Apr-20 A | 23-Apr-20 A | No
RW Gate Valves 2inch to 12inch |  | 27-Jan-20 A | 06-Feb-20 A
P/S_RW Gate Valves 2 inch to 12 inch | SL600 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_RW Gate Valves 2 inch to 12 inch | SL4750 | 28-Jan-20 A | 06-Feb-20 A | No
Schedule of Values |  | 2020-06-01 | 2020-07-28 |  | -82
P/S_Schedule of Values | SL1050 | 2020-06-01 | 2020-06-29 | No | -82
R/A_Schedule of Values | SL5200 | 2020-06-30 | 2020-07-28 | No | -82
ASR |  | 2020-05-31 | 2020-06-29 |  | -85
P/S_ASR | SL2500 | 2020-05-31 | 2020-05-31 | No | -85
R/A_ASR | SL6650 | 2020-05-31 | 2020-06-29 | No | -85
SWPPP |  | 03-Feb-20 A | 13-Apr-20 A
P/S_SWPPP 1 | A16780 | 03-Feb-20 A | 19-Feb-20 A | No
R/A_SWPPP 1 | A16790 | 20-Feb-20 A | 02-Mar-20 A | No
P/S_SWPPP 2 | A16800 | 03-Mar-20 A | 13-Apr-20 A | No
R/A_SWPPP 2 | A16810 | 16-Mar-20 A | 03-Apr-20 A | No
P/S_SWPPP 3 | SL2650 | 04-Apr-20 A | 07-Apr-20 A | No
R/A_SWPPP 3 | SL6800 | 08-Apr-20 A | 08-Apr-20 A | No
Valve Riser Pipe and Valve Stem Extension |  | 27-Jan-20 A | 06-Feb-20 A
P/S_ Valve Riser Pipe and Valve Stem Extension | SL650 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_ Valve Riser Pipe and Valve Stem Extension | SL4800 | 28-Jan-20 A | 06-Feb-20 A | No
Savala Equiptment |  | 03-Feb-20 A | 2020-06-29 |  | -61
P/S_Savala Equiptment | SL1100 | 03-Feb-20 A | 13-Apr-20 A | No
R/A_Savala Equiptment | SL5250 | 2020-06-01 | 2020-06-29 | No | -61
USR |  | 2020-05-31 | 2020-07-22 |  | -108
P/S_USR | SL2550 | 2020-05-31 | 2020-06-22 | No | -108
R/A_USR | SL6700 | 2020-06-23 | 2020-07-22 | No | -108
Ductile Iron Fittings - 2inch to 12inch |  | 27-Jan-20 A | 06-Feb-20 A
P/S_Ductile Iron Fittings - 2 inch to 12 inch | SL700 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_Ductile Iron Fittings - 2 inch to 12 inch | SL4850 | 28-Jan-20 A | 06-Feb-20 A | No
Hot Work Permit |  | 2020-06-01 | 2020-07-28 |  | -45
P/S_Hot Work Permit | SL1150 | 2020-06-01 | 2020-06-29 | No | -45
R/A_Hot Work Permit | SL5300 | 2020-06-30 | 2020-07-28 | No | -45
12" PVC Recycled Water Pipe |  | 03-Feb-20 A | 11-May-20 A
P/S_12"" PVC Recycled Water Pipe 2 | SL2600 | 03-Feb-20 A | 05-May-20 A | No
P/S_12"" PVC Recycled Water Pipe 1 | A16820 | 03-Feb-20 A | 04-May-20 A | No
R/A_12"" PVC Recycled Water Pipe 2 | SL6750 | 03-Mar-20 A | 11-May-20 A | No
R/A_12"" PVC Recycled Water Pipe 1 | A16830 | 03-Mar-20 A | 11-May-20 A | No
FAA 7460 (Duration of Project) |  | 2020-06-01 | 2020-07-28 |  | -82
P/S_FAA 7460 | SL1200 | 2020-06-01 | 2020-06-29 | No | -82
R/A_FAA 7460 | SL5350 | 2020-06-30 | 2020-07-28 | No | -82
LADWP Manholes |  | 2020-06-01 | 2020-07-28 |  | -85
P/S_LADWP ManHoles (Vaults) | SL1400 | 2020-06-01 | 2020-06-29 | Yes | -85
R/A_LADWP ManHoles (Vaults) | SL5550 | 2020-06-30 | 2020-07-28 | Yes | -85
Rubber Seated Butter Fly Valve |  | 03-Feb-20 A | 22-May-20 A
P/S_Rubber Seated Butter Fly Valve | SL2950 | 03-Feb-20 A | 15-May-20 A | No
R/A_Rubber Seated Butter Fly Valve | SL7100 | 03-Mar-20 A | 22-May-20 A | No
Swith Pads & Vaults |  | 2020-06-01 | 2020-07-28 |  | -20
P/S_Switch Pad & Vault | SL1450 | 2020-06-01 | 2020-06-29 | No | -20
R/A_ Switch Pad & Vault | SL5600 | 2020-06-30 | 2020-07-28 | No | -20
Bolt Nut Kit and gaskets |  | 27-Jan-20 A | 05-Feb-20 A
P/S_Bolt Nut Kit and Gaskets | SL3050 | 27-Jan-20 A | 27-Jan-20 A | No
R/A_Bolt Nut Kit and Gaskets | SL7200 | 03-Feb-20 A | 05-Feb-20 A | No
Griffith Equipment Rates |  | 03-Feb-20 A | 2020-06-29 |  | 295
P/S_Griffith Equipment Rates | SL800 | 03-Feb-20 A | 23-Mar-20 A | No
R/A_Griffith Equipment Rates | SL4950 | 2020-06-01 | 2020-06-29 | No | 295
Contractor Representative |  | 23-Jan-20 A | 20-Feb-20 A
P/S_Contractor Representative | SL2700 | 23-Jan-20 A | 23-Jan-20 A | No
R/A_Contractor Representative | SL6850 | 27-Jan-20 A | 20-Feb-20 A | No
Agency Trailer Layout |  | 2020-06-01 | 2020-07-28 |  | -82
P/S_Agency Trailer Layout | SL1500 | 2020-06-01 | 2020-06-29 | No | -82
R/A_Agency Trailer Layout | SL5650 | 2020-06-30 | 2020-07-28 | No | -82
Type 1 & 2 Chain Link Fence |  | 03-Feb-20 A | 02-Mar-20 A
P/S_Type 1 & 2 Chain Link Fence | SL1550 | 03-Feb-20 A | 05-Feb-20 A | No
R/A_Type 1 & 2 Chain Link Fence | SL5700 | 02-Mar-20 A | 02-Mar-20 A | No
Pedestrian Fence and Turnstile |  | 03-Feb-20 A | 23-Apr-20 A
P/S_Pedestrian Fence and Turnstile 1 | A16840 | 03-Feb-20 A | 05-Feb-20 A | No
R/A_Pedestrian Fence and Turnstile 1 | A16850 | 06-Feb-20 A | 27-Feb-20 A | No
P/S_Pedestrian Fence and Turnstile 2 | SL1600 | 27-Feb-20 A | 06-Apr-20 A | No
R/A_Pedestrian Fence and Turnstile 2 | SL5750 | 07-Apr-20 A | 23-Apr-20 A | No
K-12 Crash Gate |  | 03-Feb-20 A | 26-Feb-20 A
P/S_K-12 Crash Gate | SL1650 | 03-Feb-20 A | 06-Feb-20 A | No
R/A_K-12 Crash Gate | SL5800 | 10-Feb-20 A | 26-Feb-20 A | No
Tymetal Slide Gates |  | 03-Feb-20 A | 26-Feb-20 A
P/S_Tymetal Slide Gates | SL1700 | 03-Feb-20 A | 06-Feb-20 A | No
R/A_Tymetal Slide Gates | SL5850 | 10-Feb-20 A | 26-Feb-20 A | No
Mechanical QCM |  | 03-Feb-20 A | 19-Feb-20 A
P/S_Mechanical QCM | SL1750 | 03-Feb-20 A | 06-Feb-20 A | No
R/A_Mechanical QCM | SL5900 | 10-Feb-20 A | 19-Feb-20 A | No
Electrical QCM |  | 03-Feb-20 A | 19-Feb-20 A
P/S_Electrical QCM | SL1800 | 03-Feb-20 A | 06-Feb-20 A | No
R/A_Electrical QCM | SL5950 | 10-Feb-20 A | 19-Feb-20 A | No
Alternate QCM |  | 03-Feb-20 A | 19-Feb-20 A
P/S_Alternate QCM | SL1850 | 03-Feb-20 A | 06-Feb-20 A | No
R/A_Alternate QCM | SL6000 | 10-Feb-20 A | 19-Feb-20 A | No
Precast Electrical and Communications Structures |  | 03-Feb-20 A | 20-Mar-20 A
P/S_Precast Electrical and Communications Structures | SL1900 | 03-Feb-20 A | 07-Feb-20 A | No
R/A_Precast Electrical and Communications Structures | SL6050 | 03-Mar-20 A | 20-Mar-20 A | No
Prefabricated Sally Port & Pre-Screen Access Posts |  | 01-Jan-20 A | 2020-06-29 |  | 36
P/S_Prefabricated Sally Port & Pre-Screen Access Posts Bldgs | SL1950 | 01-Jan-20 A | 03-Jan-20 A | No
R/A_Prefabricated Sally Port & Pre-Screen Access Posts Bldgs | SL6100 | 2020-06-01 | 2020-06-29 | No | 36
Steel Canopy |  | 03-Feb-20 A | 04-Mar-20 A
P/S_Steel Canopy | SL2000 | 03-Feb-20 A | 13-Feb-20 A | No
R/A_Steel Canopy | SL6150 | 03-Mar-20 A | 04-Mar-20 A | No
Griffith Tier 4 Final Equipment List |  | 03-Feb-20 A | 10-Mar-20 A
P/S_Griffith Tier 4 Final Equipment List | SL2150 | 03-Feb-20 A | 24-Feb-20 A | No
R/A_Griffith Tier 4 Final Equipment List | SL6300 | 03-Mar-20 A | 10-Mar-20 A | No
Standpipe Vent |  | 03-Feb-20 A | 31-Mar-20 A
P/S_Standpipe Vent 1 | A16860 | 03-Feb-20 A | 25-Feb-20 A | No
R/A_Standpipe Vent 1 | A16870 | 26-Feb-20 A | 20-Mar-20 A | No
P/S_Standpipe Vent 2 | SL2200 | 20-Mar-20 A | 20-Mar-20 A | No
R/A_Standpipe Vent 2 | SL6350 | 23-Mar-20 A | 31-Mar-20 A | No
Injury and Illness Prevention Plan (IIPP) |  | 03-Feb-20 A | 10-Apr-20 A
P/S_Injury and Illness Prevention Plan (IIPP) | SL2250 | 03-Feb-20 A | 10-Mar-20 A | No
R/A_Injury and Illness Prevention Plan (IIPP) | SL6400 | 03-Mar-20 A | 10-Apr-20 A | No
SAAP QCP |  | 03-Feb-20 A | 14-Apr-20 A
P/S_SAAP QCP 1 | A16880 | 03-Feb-20 A | 19-Feb-20 A | No
R/A_SAAP QCP 1 | A16890 | 20-Feb-20 A | 02-Mar-20 A | No
P/S_SAAP QCP 2 | SL2050 | 03-Mar-20 A | 10-Mar-20 A | No
R/A_SAAP QCP 2 | SL6200 | 11-Mar-20 A | 14-Apr-20 A | No
AOA Fence Barrier- Rebar Shop Drawings |  | 03-Feb-20 A | 23-Mar-20 A
P/S_AOA Fence Barrier- Rebar Shop Drawings | SL4050 | 03-Feb-20 A | 13-Mar-20 A | No
R/A_AOA Fence Barrier- Rebar Shop Drawings | SL8200 | 03-Mar-20 A | 23-Mar-20 A | No
K-12 Crash Gate- Rebar Shop Drawings |  | 2020-06-01 | 2020-07-28 |  | 167
P/S_K-12 Crash Gate- Rebar Shop Drawings | SL3450 | 2020-06-01 | 2020-06-29 | No | 167
R/A_K-12 Crash Gate- Rebar Shop Drawings | SL7600 | 2020-06-30 | 2020-07-28 | No | 167
Slab Cover Vault- Rebar Shop Drawings |  | 2020-06-01 | 2020-07-28 |  | 76
P/S_Slab Cover Vault- Rebar Shop Drawings | SL3700 | 2020-06-01 | 2020-06-29 | No | 76
R/A_Slab Cover Vault- Rebar Shop Drawings | SL7850 | 2020-06-30 | 2020-07-28 | No | 76
Light Pole Foundations- Rebar Shop Drawings |  | 2020-06-01 | 2020-07-28 |  | -61
P/S_Light Pole Foundations- Rebar Shop Drawings | SL3750 | 2020-06-01 | 2020-06-29 | No | -61
R/A_Light Pole Foundations- Rebar Shop Drawings | SL7900 | 2020-06-30 | 2020-07-28 | No | -61
Planter Wall- Rebar Shop Drawings |  | 2020-06-01 | 2020-07-28 |  | 109
P/S_Planter Wall- Rebar Shop Drawings | SL3800 | 2020-06-01 | 2020-06-29 | No | 109
R/A_Planter Wall- Rebar Shop Drawings | SL7950 | 2020-06-30 | 2020-07-28 | No | 109
Canopy Foundations- Rebar Shop Drawings |  | 2020-06-01 | 2020-06-29 |  | 113
P/S_Canopy Foundations- Rebar Shop Drawings | SL3850 | 2020-06-01 | 2020-06-01 | No | 113
R/A_Canopy Foundations- Rebar Shop Drawings | SL8000 | 2020-06-01 | 2020-06-29 | No | 113
AA OSF Building Retaining Wall- Rebar Shop Drawings |  | 03-Feb-20 A | 2020-08-24 |  | 28
P/S_AA OSF Building Retaining Wall- Rebar Shop Drawings 1 | A16920 | 03-Feb-20 A | 13-Mar-20 A | No
R/A_AA OSF Building Retaining Wall- Rebar Shop Drawings 1 | A16930 | 16-Mar-20 A | 31-Mar-20 A | No
P/S_AA OSF Building Retaining Wall- Rebar Shop Drawings 2 | A16940 | 01-Apr-20 A | 27-May-20 A | No
R/A_AA OSF Building Retaining Wall- Rebar Shop Drawings 2 | A16950 | 2020-06-01 | 2020-06-26 | No | 28
P/S_AA OSF Building Retaining Wall- Rebar Shop Drawings 3 | SL3900 | 2020-06-29 | 2020-07-24 | No | 28
R/A_AA OSF Building Retaining Wall- Rebar Shop Drawings 3 | SL8050 | 27-Jul-20* | 2020-08-24 | No | 28
Pump Pads Pump House- Rebar Shop Drawings |  | 2020-06-01 | 2020-07-28 |  | -31
P/S_Pump Pads Pump House- Rebar Shop Drawings | SL3950 | 2020-06-01 | 2020-06-29 | No | -31
R/A_Pump Pads Pump House- Rebar Shop Drawings | SL8100 | 2020-06-30 | 2020-07-28 | No | -31
Tank Pads at Pump House- Rebar Shop Drawings |  | 2020-06-01 | 2020-07-28 |  | -16
P/S_Tank Pads at Pump House- Rebar Shop Drawings | SL4000 | 2020-06-01 | 2020-06-29 | No | -16
R/A_Tank Pads at Pump House- Rebar Shop Drawings | SL8150 | 2020-06-30 | 2020-07-28 | No | -16
3rd Party Inspection - On Site |  | 23-Jan-20 A | 24-Feb-20 A
P/S_3rd Party Inspection - On Site | SL2750 | 23-Jan-20 A | 23-Jan-20 A | No
R/A_3rd Party Inspection - On Site | SL6900 | 27-Jan-20 A | 24-Feb-20 A | No
Safety Manager |  | 20-Jan-20 A | 20-Feb-20 A
P/S_Safety Manager | SL2800 | 20-Jan-20 A | 23-Jan-20 A | No
R/A_Safety Manager | SL6950 | 03-Feb-20 A | 20-Feb-20 A | No
Site Specific Safety Plan |  | 21-Jan-20 A | 21-Feb-20 A
P/S_Site Specific Safety Plan 1 | A16900 | 21-Jan-20 A | 23-Jan-20 A | No
R/A_Site Specific Safety Plan 1 | A16910 | 24-Jan-20 A | 03-Feb-20 A | No
P/S_Site Specific Safety Plan 2 | SL2850 | 04-Feb-20 A | 04-Feb-20 A | No
R/A_Site Specific Safety Plan 2 | SL7000 | 04-Feb-20 A | 21-Feb-20 A | No